## Project Charter
Project Charter for Group 6
Project Title: JAM'N
Project Manager | James Johnston
Project start date: | 2026-08-24 | Project end date: | 2026-09-25
E-Commerce Business Idea Concept
An e-commerce website designed to promote and commercialise music created by local South African artists. The central problem the project addresses is that emerging local artists can struggle to gain exposure beyond their existing social circles, while potential listeners may have difficulty discovering new and experimental local music.
Project objectives: This section addresses how the project ties into the group's strategic e-commerce goals, and includes the project objectives that support those goals. |  |  |  | Benefits: Benefits to potential stakeholders by doing the project .
1 A functioning music and video player |  |  |  | 1 Ticket sellers get more new, possibly reocorring clients
2 Spread SA music (artists specifically) |  |  |  | 2 Artists get more media exposure and opportunities
3 Promote local artists and their events |  |  |  | 3 Listeners get to connect with people of their country
4 Payment system that aids the artists while generating income for us as well |  |  |  | 4 A community based on music
Stakeholder Requirements: |  |  |  | Project stakeholders:
A love for the people of our country and the music that they produce. A connection to venues where these artists may perform |  |  |  | South Africans in general, artists, experimental listeners, music venues and ticket salesmen
Deliverables: List the core requirements of your e-commerce website. This includes functional and non-functional requirements.
Functioning log in |  | Consistent styling |  | Proper integration of frontend and backend | Working event calander
Functional music player |  | Functioning payment system |  | Proper display of profiles | Professional styling
All buttons functional |  | Properly linked pages |  | Seperation of creator and listener sides | Active links
Roles and responsibilities:
Name | Surname | Student number | Role | Cellphone | Email
James | Johnston | N/A | Team Manager, Figma Designer, Frontend Dev | 064 855 1399 | jaston2706@gmail.com
Maiesha | Moohan | N/A | Frontend Dev | 074 769 1854 | maieshamoohan@gmail.com
Ahlumile | Totose | N/A | Design Assistant, Backend Dev, Frontend Support | 069 403 1935 | totoseahlumile@gmail.com
Nuriyah | Davids | N/A | Documentation, Charter, Backend Dev | 065 921 5802 | nuriyahdavids2006@gmail.com
N/A
Scope: |  |  |  | Out of Scope:
Artist profiles, genre filter, playable music, linked external music profiles |  |  |  | Scraper
Risks: |  |  | Constraints: |  | Mitigation:
Competition with other music websites like Spotify, Rights to artists' music, technical difficulties aka server crashes(payfast) |  |  | Focus on only English songs for now, to keep things simple. Only use songs that have music videos. |  | Personalisation of music based on the user input
Assumptions: Known factors about the project that are not flexible.
Functional payment system, user input, variety of artists and songs
Comments/Notes: